## Q&A Responses
No. | Question | Topic | Answer
Note | We have created a minimal runnable prototype with dummy data for your reference as follows. This prototype was generated entirely using ChatGPT with ToR. Since we have very limited time for this PoC, it is recommended to utilize the benefit of the latest AI in the development process to minimize the time and cost. https://github.com/yoichikogure/motapoc/
Q.1 | Absolute Budget Ceiling: The RFP mentions an "Absolute Budget Ceiling" in Section 17.2. Could you please specify the exact numerical value of this ceiling in USD? This is critical to ensure our financial proposal is compliant and not subject to immediate disqualification. | Budget ceiling | Absolute Budget Ceiling cannot be disclosed. Note that the budget is quite limited because the nature of this PoC is to develop a prototype.
Q.2 | Taxation & Duties: Please confirm if the budget ceiling is inclusive of the 16% Sales Tax and all local stamp duties/governmental fees, or if these should be budgeted separately. | Tax / duties treatment | The budget ceiling is inclusive of all taxes and duties. This means entire payment amount from JDS must not exceed the budget ceiling.
Q.3 | Data Readiness & Cleanliness: Section 7 of the ToR states that MoTA/JTB will provide datasets. Are these datasets already "cleansed" and "structured," or is the Joint Team expected to perform extensive Data Cleaning and ETL (Extract, Transform, Load) processes? | Data cleaning and ETL responsibility | The Joint Team is responsible for data cleaning, validation, normalization, harmonization, and repeatable ETL. Subsystem A explicitly requires CSV import, automated cleansing, duplicate prevention, error reporting, and loading into PostgreSQL/PostGIS. The MoTA/JTB datasets are exported data from existing systems and they are basically clean.
Q.4 | API vs. Static Access: Will the data be shared via live API integration with MoTA/JTB systems, or will it be provided as static historical files? | Data exchange method / integrations | The PoC is standalone and must not integrate with existing operational systems. The ToR assumes static CSV files exported from MoTA/JTB systems, not live API integration.
Q.5 | Success Metrics: What are the specific technical KPIs (e.g., Prediction Accuracy, F1-Score) that will be used during the User Acceptance Test (UAT) to define the "success" of the AI models? | PoC KPIs / acceptance metrics | The acceptance KPIs are those in the ToR: national-level 12-month back-test MAPE not exceeding 20%; governorate-level MAPE/MAE/RMSE reported and interpreted; indicator reproducibility; required dashboard pages/features operating without critical error; responsive performance under normal PoC use; and complete deployment/handover, documentation, training, and formal acceptance by MoTA. No F1-score is specified.
Q.6 | Pre-existing IP vs. Project IP: Our firm utilizes proprietary consulting methodologies and pre-developed code modules. Could you clarify that the IP transfer to MoTA applies only to the "specific scripts and outputs developed during this PoC" and does not include the firm’s pre-existing intellectual property? | Pre-existing IP carve-out | The ToR states that intellectual property of the developed PoC solution belongs to MoTA, including datasets, scripts, and source codes. No carve-out for bidder pre-existing proprietary modules is stated in the ToR, so proposals should comply with the ToR as written.
Q.7 | Liability Cap: Given that AI models are probabilistic by nature, is there a defined "Liability Cap" regarding the accuracy of the investment prioritization recommendations provided by the PoC? | Liability cap | Since this is a PoC, no liability cap is defined in the ToR.
Q.8 | Lead Firm Definition: Does a consulting and training firm (registered at CCD) qualify as the "Private IT Company" lead, provided it demonstrates the required software development and AI expertise in its profile? | Eligibility of a consulting/training firm as lead | A consulting/training firm qualifies only if it also meets the ToR requirements for the private IT company: Jordanian CCD registration, relevant technology-service licensing, valid permit, a major IT development team in Jordan, and the required AI/system-development experience. A consulting profile alone is not sufficient.
Q.9 | Gender Appreciation: Could you clarify the weight/points assigned to the "additional appreciation" for female participation? Also, does this apply to leadership roles (e.g., Project Manager) or the overall team composition? | Gender consideration / scoring | See answer to Q.48.
Q.10 | Source Code Handover: Is the requirement to hand over the "Executable Solution" or the full "Documented Source Code" including the training environment for the AI models? | IP ownership and source-code/model handover | See answer to Q.41.
Q.11 | Absolute Ceiling: The RFP states that any Financial Proposal exceeding the "absolute ceiling of budget" will be disqualified. Could you please provide the specific value of this ceiling to ensure our compliance? | Budget ceiling | See answer to Q.1.
Q.12 | Infrastructure Costs: The Financial Proposal form (FIN-2) lists "GPU cloud service" as a reimbursable item. However, the technical specifications for the backend state it should run on standard CPU infrastructure. Should we include cloud hosting costs in our reimbursable expenses, and is there a preferred provider? | GPU cloud / hosting cost assumption | The delivered PoC must run on standard CPU infrastructure and be deployed on-premise at MoTA on a contractor-procured server, then migrated to MoDEE. The ToR does not require cloud hosting, GPU services, or any preferred cloud provider; proposals should follow the on-prem architecture defined in the ToR.
Q.13 | Data Readiness: Are the historical tourism demand (site visits, occupancy) and supply (rooms, beds) datasets currently available in a structured format (e.g., SQL, CSV) or will they require significant manual extraction from reports? | Data cleaning and ETL responsibility | See answer to Q.3.
Q.14 | GIS Data: Is the transport network and geographic boundary data already available in standard GIS formats (e.g., Shapefiles or GeoJSON)? | Official GIS layers / GIS-ready reference data; Data types and formats | See answers to Q.120, and Q.141.
Q.15 | Data Dictionary: Can a sample data dictionary or schema be provided to help us better estimate the cleansing effort required for Subsystem A? | Sample data / schemas before bid | See answer to Q.22.
Q.16 | Foreign Participation: For the "20% work limit" on foreign companies, is this measured by the total contract value or the total person-months of the project? | Foreign company 20% work limit | The ToR says foreign companies may not lead and may not render more than 20% of the required work, but it does not define the exact measurement formula. For compliance, bidders should keep the foreign share clearly below 20% and explain the basis transparently in effort and commercial terms.
Q.17 | Academic Partner Role: Is there a minimum required level of effort (man-months) expected from the Academic AI Researcher to satisfy the evaluation criteria? | Academic AI researcher minimum effort | No minimum man-month commitment is stated. The academic AI researcher must, however, be substantively engaged enough to perform the required advisory/validation roles, participate in meetings, and support the bi-weekly and final deliverables.
Q.18 | Accessibility Ratings: The TOR mentions "accessibility ratings" should only be included if they can be produced reliably. Are there specific accessibility parameters MoTA is most interested in (e.g., proximity to major roads vs. travel time)? | Accessibility rating formula; Accessibility rating data readiness / optionality | See answers to Q.30, and Q.27.
Q.19 | Deployment: Does MoDEE have a preferred internal server environment for the "locally hosted web service" option? | MoDEE target environment / provisioning access | See answer to Q.32.
Q.20 | It was mentioned that a joint team should be formed to participate, and I would like to clarify whether the AI researcher must be affiliated with a university, or if they can be part of the same company. | Mandatory joint team and researcher affiliation | It is acceptable that the AI researcher is from the same company, but the researcher will be evaluated based on his/her AI academic research background as described in the ToR such as major published research papers.
Q.21 | Given that the project is described as a public–private–academic collaboration, is this structure mandatory, or is it acceptable for all team members to come from the same company? | Mandatory joint team and researcher affiliation | See answer to Q.20.
Q.22 | Clarification on Data Format: The TOR states that data will be provided via CSV files. Can the project owner provide a sample of the actual CSV files (or their detailed schemas/column definitions) from MoTA/JTB before the proposal stage? This is critical for accurately estimating the complexity of the ETL process and mapping logic. | Sample data / schemas before bid | See "Data columns" tab for data structure for monthly site visitors. Other datasets have similar "exported" CSV structure from existing systems at MoTA.
Q.23 | Data Completeness & Historical Depth: The forecasting model requires historical data for back-testing (e.g., 12 months withheld). What is the expected historical depth (number of years of monthly data) available for the key indicators (visitor arrivals, site visits, occupancy rates)? Is the data consistent and complete for all governorates and the specified tourism clusters (Petra, Wadi Rum, etc.)? | Historical depth and completeness | Available historical depth of datasets is monthly data from the year 2010 to 2025. Some governorates data may not be complete, though.
Q.24 | Geospatial Data Quality: The TOR mentions that some datasets have geospatial coordinates. What is the expected quality and completeness of this coordinate data (e.g., percentage of hotels with accurate lat/lon)? Are there established, standardized naming conventions for governorates, regions, and tourism sites across all datasets? | Geospatial data quality / naming consistency | Most of the geospatial data will be exported data from ArcGIS Desktop (ArcMap) application currently used at MoTA. All officially registered hotels data in Jordan contains lat/lon. The accuracy of coordinates are not known. Non-registered/privately-run inns (such as AirBnB) will not be covered in this PoC.
Q.25 | Geospatial Precision: For "Accommodation locations," what is the current percentage of records that already include valid geographical coordinates versus those that only have address text? | Geospatial data quality / naming consistency | See answer to Q.24.
Q.26 | Adjustable Forecasting Horizon: The TOR states the forecasting horizon shall be adjustable by the user (e.g., 6, 12, 24 months) but should not accept too far a horizon. What is the maximum acceptable horizon that the system should allow? This impacts the forecasting model's design and the communication of its inherent uncertainty. | Maximum forecasting horizon | The ToR requires a default 12-month horizon and says users may adjust to horizons such as 6 or 24 months, but not excessively far because of reliability risk. Practical maximum would be up to 24 months.
Q.27 | "Accessibility Rating" in Investment Scoring: Section 3.2.2(6) mentions that an "accessibility rating" will be calculated using transport network data (roads, airlines). Is this transport network data confirmed to be available in a GIS-ready format from MoTA/JTB at the start of the project? If not, should this feature be considered out-of-scope or developed using publicly available data (e.g., OpenStreetMap)? | Accessibility rating data readiness / optionality | It is confirmed that MoTA/JTB already have all required GIS-ready data in either ArcGIS format or Geo-JSON format.
Q.28 | "Historical Versions" of Transport Data: The requirement to keep all historical versions of transport network data is noted. What is the expected update frequency for this data? This requirement adds complexity to the data store and ETL process. | Historical versions of transport data | The ToR requires the data store to retain historical versions of transport-network data with effective dates, but it does not specify an update frequency. Proposals should therefore design simple versioning that can accommodate periodic (and manual) replacement whenever updated data is provided.
Q.29 | Simulation Complexity: For the "what-if" scenarios, should the system support simultaneous changes (e.g., increasing both beds and visitors) or only one variable at a time? | Simultaneous / phased scenarios | The minimum scope is one user-defined scenario against the forecasted baseline for either capacity change or demand change. Simultaneous multi-variable or phased multi-step scenarios are not required by the ToR and should not be assumed as part of the PoC scope.
Q.30 | Accessibility Rating Logic: The TOR lists this as a "reduced-scope" item. Does the owner have a preferred formula for calculating "accessibility" (e.g., travel time to nearest airport/highway), or is the contractor expected to propose the logic? | Accessibility rating formula | No preferred accessibility formula is available and it's up to contractor's proposal as well as up to discussions with MoTA/JTB.
Q.31 | Dashboard User Base: How many concurrent users should the "Staging Server" and final MoDEE deployment support? | Expected concurrent users | Since this is a PoC prototype, maximum number of concurrent users would be around 10.
Q.32 | Who is responsible for the virtual server environment at MoDEE? Will the contractor be provided with access to provision the server, or will that be handled by MoDEE's IT team? | MoDEE target environment / provisioning access | Provision of virtual server will be handled by MoDEE IT team.
Q.33 | What is the timeline for this migration? Is it expected to occur within the 6-month PoC period, or after the formal handover? This affects the final acceptance criteria. | Migration timeline | Migration/final deployment to MoDEE is expected within the 6-month PoC period. It is strongly recommended to employ easy-to-migrate technology stack such as Docker containers for the development.
Q.34 | User Administration: Section 4.4 mentions a "basic access control (username/password)" as a non-functional requirement. Should the system include a simple user administration module for MoTA to manage these credentials, or is a single shared login acceptable for the PoC? | User administration / roles | See answer to Q.139.
Q.35 | MoDEE Migration: What is the specific virtualization environment at the MoDEE data center (e.g., VMware, Nutanix, Hyper-V)? Knowing this is vital for ensuring the "Staging Server" is compatible with the final migration. | MoDEE target environment / provisioning access | See answer to Q.32.
Q.36 | KPI Flexibility: The 20% MAPE (Mean Absolute Percentage Error) target for forecasting is a firm requirement. If the historical data provided is highly volatile or insufficient, is there a process to renegotiate this KPI during the first two months of data cleansing? | KPI renegotiation if data is poor | It would be possible to renegotiate the KPI if the historical data is highly volatile or insufficient.
Q.37 | "How to Update Data Monthly" Procedure: The TOR requests a procedure for MoTA analysts to update data monthly. What is the expected technical skill level of the MoTA staff who will perform this task? This will dictate the level of detail required in the Administrator Manual (e.g., command-line scripts vs. a simple UI-based upload feature, which is already mentioned as a button in Subsystem A). | Expected skill level for monthly data updates | The ToR assumes MoTA analysts—not developers—will update data monthly, and therefore expects a clear, minimally technical procedure, including a dashboard upload button plus administrator manual and training. The update process should be UI-led wherever possible, with scripts/documentation as backup.
Q.38 | Definition of "Unpredictable Events": The MAPE target of ≤20% includes an exemption for "unpredictable socioeconomic or geopolitical events." How will this be evaluated? For example, if a regional event causes a sudden drop in tourism that was not in the historical training data, will that period be excluded from the KPI calculation? A clear definition is needed to avoid disputes during acceptance testing. | Unpredictable events / structural breaks | Any sudden change due to unforeseen events can be exclueded from the KPI evaluation.
Q.39 | Governorate-Level Forecast Evaluation: For governorates with limited data, the TOR states "no fixed numeric threshold is imposed." Should the contractor still propose internal quality gates or targets for these areas in their proposal to demonstrate commitment to quality, or is simply reporting the metrics sufficient? | Governorate-level forecast metrics | Governorate-level MAPE, MAE, and RMSE must be reported and interpreted, but no fixed numeric acceptance threshold is imposed at governorate level. Reporting the metrics with explanation of data limitations is sufficient.
Q.40 | Single Point of Contact (Focal Point): Section 6.1 requires a single point of contact for the Joint Team. Will this focal point have the authority to make technical and financial decisions on behalf of both the private company and the academic researcher, or will they primarily serve as a communication coordinator? | Unified focal point | The Joint Team must have one unified focal point as the single official interface to stakeholders. The proposal should identify that focal point and explain how the private company and academic partner coordinate through that person. In other words, any coordination between academic researcher and private company must be done within the Joint Team.
Q.41 | Intellectual Property (IP): Section 12 states that IP belongs to MoTA. Does this include the source code for the AI forecasting and simulation models, as well as the trained model artifacts? This is a standard point to confirm. | IP ownership and source-code/model handover | Full documented source code and scripts are required, not merely an executable. The handover package includes preprocessing scripts, analytics/forecasting/simulation scripts, dashboard source code, configuration files, installation instructions, and, as part of the delivered PoC solution, the model artifacts needed to operate the system.
Q.42 | Partial Payments (Section 13): The TOR mentions that partial payments may be possible on a tangible deliverables basis. Can the project owner provide guidance on the expected number of payment milestones or the specific deliverables that would trigger a payment? This is important for cash flow planning. | Partial payments / performance-based payment | It's up to negotiation between the contractor and JDS. Based on the experiences from past PoCs, the number of partical payments should not exceed 4.
Q.43 | Performance-Based Payment: The TOR states that "any portion... that fails to satisfy the agreed KPIs... will not be paid". Does this apply to the entire contract value, or are there milestone payments for successful data integration (Subsystem A) even if the forecast (Subsystem B) exceeds the 20% error margin? | Partial payments / performance-based payment | See answer to Q.42. Partial payments based on subsystem is also possible.
Q.44 | Hardware Procurement: The contractor will include the server PC in the quotation. Is this PC expected to be handed over to MoTA as a permanent asset, or is it strictly for the PoC duration? | Server ownership / hardware handover | The server PC is part of the contractor's quotation and is intended for on-prem deployment at MoTA as the staging server, with later migration to MoDEE. It should therefore be treated as a project deliverable/asset to hand over, not as temporary contractor equipment.
Q.45 | The TOR strongly prefers open-source software. Is use of commercial software allowed, such as: - ArcGIS - Power BI If yes: Will license cost be reimbursed? | Open-source vs proprietary / enterprise tools | No.
Q.46 | Clarification on "Unified Contact Point": In the proposal, should the Joint Team explicitly name the "focal point" and describe the internal communication and decision-making structure between the private company and the academic researcher? What level of detail is expected? | Unified focal point | See answer to Q.40.
Q.47 | Will a draft contract or key contractual clauses (beyond Section 9) be shared with shortlisted bidders? | Draft contract / additional contract clauses | No.
Q.48 | Regarding Gender consideration (Section 10): Could you kindly clarify how female participation will be evaluated in the technical and financial scoring? | Gender consideration / scoring | Explicit female participation to key engineers or AI researcher will gain some additional points in the evaluation.
Q.49 | The ToR specifies that the private IT company must have a development team where at least 80% are Jordanian nationals or permanent residents. Could you please clarify whether this requirement applies to the entire company workforce, or specifically the project delivery/development team assigned to this PoC? | 80% Jordanian requirement | The 80% requirement applies to entire company workforce.
Q.50 | If the requirement that at least 80% of the team be Jordanian nationals applies to the development team: •Jordanian freelance or contracted resources (e.g., independent consultants) are acceptable, and whether such resources can be counted toward the 80% requirement? | Freelancers counted toward Jordanian team ratio | Jordanian freelance/contracted personnel assigned to the delivery team may be counted only if they are genuinely part of the project team and meet the Jordanian national or permanent-resident criterion, with their role and availability clearly documented.
Q.51 | Could you please provide details on the datasets to be used in the PoC, including: •Estimated data volume and historical coverage (time span) •Data structure and format (e.g., sample schemas for CSV files) •Data completeness and quality (e.g., missing values, inconsistencies) •Availability of geospatial attributes (coordinates for hotels/sites) | Historical depth and completeness; Geospatial data quality / naming consistency; Exact minimum datasets in scope | See answers to Q.23, Q.24, and Q.124.
Q.52 | The RFP mentions an absolute budget ceiling above which proposals will be disqualified. Could you kindly share the budget ceiling allocated for this PoC? | Budget ceiling | See answer to Q.1.
Q.53 | Considering that the PoC performance is evaluated based on KPIs such as forecasting accuracy, could you clarify: •How will KPI achievement be validated and approved? •Whether partial acceptance and payment are possible in case certain KPIs are not fully met due to data limitations? | PoC KPIs / acceptance metrics; Partial payments / performance-based payment; Impact of data quality on KPI evaluation | See answers to Q.5, Q.42, and Q.123.
Q.54 | What exact datasets are currently available at MoTA/JTB? Specifically, could you provide a list of available tables or files, including their column definitions, data types, date formats, and encoding (e.g., UTF-8)? | Exact minimum datasets in scope; Data types and formats; Data models / standards / naming rules | See answers to Q.124, Q.141, and Q.142.
Q.55 | How many years of historical data are available per dataset particularly for visitor demand, site visits, and hotel occupancy? This is critical for assessing the feasibility and reliability of the forecasting module. | Historical depth and completeness | See answer to Q.23.
Q.56 | Are hotel and accommodation location coordinates already geocoded (i.e., latitude/longitude available), or is only address-level information available? | Geospatial data quality / naming consistency | See answer to Q.24.
Q.57 | What is the current known state of data quality across the available datasets? Are there known gaps, missing periods, inconsistencies in naming conventions, or incomplete governorate coverage? | Geospatial data quality / naming consistency; Impact of data quality on KPI evaluation | See answers to Q.24, and Q.123.
Q.58 | Would it be possible to provide a sample dataset (even anonymized or partial) prior to contract signing, so that the Joint Team can assess data structure and feasibility before finalizing the technical proposal? | Sample data / schemas before bid | See answer to Q.22.
Q.59 | What naming conventions and IDs does MoTA/JTB currently use for governorates and regions? Is there an official reference list or codebook that the system should align to? | Geospatial data quality / naming consistency; Data models / standards / naming rules | See answers to Q.24, and Q.142.
Q.60 | The historical tourism data likely contains structural breaks due to exceptional events such as the COVID-19 pandemic. Should the forecasting model be expected to handle such structural breaks automatically, or will MoTA/JTB provide guidance on which periods should be manually excluded or flagged prior to model training? | Unpredictable events / structural breaks | See answer to Q.38.
Q.61 | Should the proposal assume that the provided datasets are sufficient to compute all required indicators, classifications, and priority scores, or are there known gaps/optional fields that bidders should account for? | Assumption about dataset sufficiency / readiness | For proposal purposes, assume MoTA/JTB will provide the core datasets listed in the ToR and that all input datasets are intended to be ready at the beginning of the PoC. Exact completeness/quality should still be confirmed during kickoff and early data assessment, and where detail is incomplete the ToR already allows reduced-scope outputs or aggregation.
Q.62 | Can sample schemas or sample CSV files be shared for the expected input dataset types. | Sample data / schemas before bid | See answer to Q.22.
Q.63 | What is the expected volumne of historical coverage which will be provided as initial input? | Historical depth and completeness | See answer to Q.23.
Q.64 | Will all supporting GIS reference layers required for the PoC be provided by MoTA/JTB, and in what formats will they be delivered? | Official GIS layers / GIS-ready reference data; Data types and formats | See answers to Q.120, and Q.141.
Q.65 | Is containerized deployment acceptable (e.g. docker containers) for the PoC staging server and for the final migration environment at MoDEE data center, provided the solution remains fully documented and self-contained? | Containerization / Kubernetes; Target deployment environment | See answers to Q.184, and Q.81.
Q.66 | Could you share sample datasets or schemas for the tourism demand and accommodation supply data to be used in the PoC? | Sample data / schemas before bid | See answer to Q.22.
Q.67 | What is the historical depth (number of years) of the available datasets? | Historical depth and completeness | See answer to Q.23.
Q.68 | What level of geographic granularity is available (e.g., governorate, city, site-level)? | Geographic granularity | See answer to Q.91.
Q.69 | Are geospatial layers (e.g., administrative boundaries, site/hotel coordinates) already available? | Official GIS layers / GIS-ready reference data | See answer to Q.120.
Q.70 | Should we expect multiple data sources requiring reconciliation, or a single standardized dataset per category? | Data cleaning and ETL responsibility; Data exchange method / integrations | See answers to Q.3, and Q.4.
Q.71 | To what extent should we expect inconsistencies (e.g., missing values, naming variations) in the datasets? | Geospatial data quality / naming consistency | See answer to Q.24.
Q.72 | Are there any existing data standards or naming conventions that should be followed? | Geospatial data quality / naming consistency; Data models / standards / naming rules | See answers to Q.24, and Q.142.
Q.73 | Who are the primary users of the system (e.g., policy makers, analysts)? | Expected user groups | See answer to Q.177.
Q.74 | What are the key decisions the system is expected to support? | Key decisions supported | The PoC is intended to support identification of tourism-demand hotspots, accommodation capacity stress or underutilization, future demand/capacity conditions, and priority zones for tourism infrastructure investment.
Q.75 | Are there existing reporting formats or dashboards currently used that should be considered? | Existing dashboards / reporting formats | No. Contractor should design the PoC around the required pages and exports specified in the ToR.
Q.76 | How should “priority investment zones” be interpreted—purely data-driven, or aligned with predefined policy considerations? | Meaning of priority investment zones | Priority investment zones are to be data-driven and transparent, based primarily on forecast demand, current capacity gap, and occupancy pressure, with rule-based justification text. Accessibility and recommended investment type are reduced-scope items to include only if they can be produced reliably.
Q.77 | Are there predefined thresholds or criteria for capacity classification (over/under-capacity), or should these be proposed by the contractor? | Indicator formulas / thresholds / approval | The ToR requires transparent, documented, configurable formulas and rules. It does not provide a complete fixed formula pack, so the contractor should propose the indicator/scoring logic, validate it with MoTA/JTB during design/UAT, and document the approved formulas and thresholds in the handover materials.
Q.78 | What level of explainability is expected for forecasting and scoring outputs? | Explainability expectation | A high level of explainability is required. Indicators, scoring, classification, and simulation must be transparent, formula-based, traceable to inputs, documented, and understandable to policy-level users.
Q.79 | Is there a preferred forecasting methodology, or is this left to the contractor’s discretion? | Forecasting methodology | Preferred methods are interpretable univariate time-series approaches such as Prophet or ARIMA/SARIMA (or equivalent additive models). Deep learning and multivariate/external-regressor models are explicitly outside the PoC scope.
Q.80 | What types of scenarios are expected in the “what-if” simulation (e.g., demand changes, capacity expansion)? | Minimum scenario / simulation scope | The minimum simulation module must let users select a target area and a future period within the supported forecast horizon, then apply either a capacity change (beds / accommodation class) or a demand change (absolute or percentage). The system must compare forecast baseline versus scenario and recalculate projected occupancy, visitors per bed, adequacy and pressure indices, capacity classification, and priority score. This is intended as a simplified, rule-based what-if capability rather than an advanced optimization engine, and no special real-time engine is required by the ToR.
Q.81 | Is there a preferred deployment environment (cloud or on-premise)? | Target deployment environment | The required deployment is on-premise: initial deployment on a contractor-procured server at MoTA, followed by migration to a virtual server at MoDEE's data center. Public cloud is not the target deployment architecture in the ToR.
Q.82 | Are there any specific security or hosting requirements to be considered? | Security / hosting constraints | Security is basic PoC-level only: internal deployment with username/password access control; no advanced enterprise security architecture is required. The delivered system must run independently without reliance on external services not included in the handover package.
Q.83 | Are there any preferred tools or frameworks for dashboard development? | Preferred dashboard architecture / tools | The ToR lists some of the recommendations for an open-source web stack such as FastAPI or Flask, PostgreSQL/PostGIS, optional GeoServer/QGIS Server, Leaflet or MapLibre, and Plotly.js or ECharts. The contractor may justify one open-source architecture consistent with the no-vendor-lock-in requirement.
Q.84 | Are there any UI/UX guidelines to be followed? | UI/UX guidance | MoTA has UI/UX guidelines and the contractor must follow them.
Q.85 | How frequently will datasets be updated (e.g., monthly)? | Update frequency | The system is expected to support periodic monthly updates. The ToR explicitly asks for a 'how to update data monthly' procedure.
Q.86 | Who will be responsible for ongoing data uploads and system usage post-delivery? | Who updates data and uses system after handover | MoTA analysts are expected to perform routine monthly data updates and use the system after handover, supported by administrator/user manuals, training, and simple import procedures.
Q.87 | Could you clarify the key performance indicators (KPIs) that will determine successful completion of the PoC? | PoC KPIs / acceptance metrics | See answer to Q.5.
Q.88 | Are there any mandatory non-system deliverables (e.g., reports, documentation, presentations)? | Mandatory non-system deliverables | Yes. Required non-system deliverables include bi-weekly progress reports, test reports, forecast-evaluation material, technical documentation, user and administrator manuals, training session/materials, and a final completion report.
Q.89 | Kindly confirm the exact three target datasets and share sample schemas or sample files for each dataset. | Exact minimum datasets in scope; Sample data / schemas before bid | See answers to Q.124, and Q.22.
Q.90 | It would be helpful to understand the known data-quality issues in each dataset, including missing values, duplicate records, inconsistent coding, incomplete historical periods, and geographic reference issues. | Geospatial data quality / naming consistency | See answer to Q.24.
Q.91 | Please confirm the required geographic granularity for the prototype analysis and outputs, and whether the analytical scope is limited to national and governorate levels only. | Geographic granularity | The minimum output granularity is national and governorate/region level, with site-level and accommodation-point mapping where such data exists. The PoC is nationwide and also highlights representative tourism clusters/corridors.
Q.92 | We would appreciate clarification on the temporal granularity required for the prototype, including whether all datasets should be harmonized to a monthly time index. | Temporal granularity | Yes. Datasets are to be harmonized to a consistent monthly time index while preserving original timestamps where relevant.
Q.93 | Please confirm the historical coverage available for the tourism demand dataset, including the number of months or years available for modeling and back-testing. | Historical depth and completeness | See answer to Q.23.
Q.94 | Kindly confirm whether the forecasting target is a national-level MAPE of 20% or less on a 12-month back-test. | PoC KPIs / acceptance metrics | See answer to Q.5.
Q.95 | Clarify whether governorate-level MAPE, MAE, and RMSE are required only for reporting and interpretation, or if they also form part of the success criteria for the prototype. | Governorate-level forecast metrics | See answer to Q.39.
Q.96 | Please confirm whether the prototype forecasting module is expected to rely solely on univariate demand forecasting methods, as stated in the TOR, or if the use of external explanatory variables is acceptable. | Forecasting methodology | See answer to Q.79.
Q.97 | We would appreciate clarification on whether there are known structural breaks, exceptional periods, or abnormal tourism patterns in the historical data that should be excluded or treated separately during model development. | Unpredictable events / structural breaks | See answer to Q.38.
Q.98 | Kindly confirm whether the formulas for visitors-per-bed ratio, occupancy pressure, growth indicators, over-capacity/under-capacity classification, and priority investment score are already defined by MoTA/JTB, or if they are to be proposed by the contractor. | Indicator formulas / thresholds / approval | See answer to Q.77.
Q.99 | If the contractor is expected to propose the indicator formulas and thresholds, please clarify who will validate and approve them, and at which stage of the prototype development they should be finalized. | Indicator formulas / thresholds / approval | See answer to Q.77.
Q.100 | It would be helpful to clarify the minimum required scope of the scenario or simulation module, including the exact user-adjustable inputs and expected output indicators. | Minimum scenario / simulation scope | See answer to Q.80.
Q.101 | Please confirm whether the prototype should include only descriptive and analytical dashboard functionality, or if it should also support user-driven scenario comparison and investment prioritization within the interface. | Dashboard must include scenario and investment functions | The prototype must do more than descriptive reporting. It must support user-driven scenario comparison against a forecast baseline and an investment explorer with ranked zones and justification.
Q.102 | Kindly confirm the required pages or views in the prototype dashboard, including whether the minimum scope includes the National Overview Page, Regional Deep-Dive Page, and Investment Explorer Page. | Required dashboard pages | At minimum, the dashboard must include the National Overview page, Regional Deep-Dive page, and Investment Explorer page.
Q.103 | Please clarify the mandatory visual outputs expected in each dashboard page, such as maps, charts, tables, rankings, forecast plots, or comparative indicators. | Mandatory outputs per page | Required outputs include national KPIs and map overlays, filters, regional time-series charts, forecast curves, computed indicators, regional maps where data exists, and an investment explorer table/map with priority score, forecast demand, capacity gap, and justification.
Q.104 | Kindly confirm whether export functions, such as CSV and image export, are mandatory components of the prototype scope. | Export / reporting outputs | CSV export is mandatory. Map snapshot/image export is desirable. An executive-summary PDF with key analytical values and charts is also required.
Q.105 | Clarify the expected logic for investment prioritization, particularly whether the prototype should automatically recommend areas or simply present scored indicators for stakeholder interpretation. | Meaning of priority investment zones | See answer to Q.76.
Q.106 | Please confirm whether the prototype must support manual cross-checking of calculated indicators against sample hand calculations, and if so, how many indicators or validation cases are expected. | Manual cross-checking of indicators | Yes. Verification must include cross-check testing with sample manual calculations, but the ToR does not specify an exact number of cases.
Q.107 | We would appreciate clarification on the testing expectations for the prototype modules, particularly for data cleansing, indicator generation, forecasting accuracy validation, and scenario simulation logic. | Testing expectations | Testing must cover functional testing, data-pipeline testing, forecast back-testing/evaluation, performance testing under typical PoC usage, and structured UAT with written feedback and issue resolution.
Q.108 | Kindly to confirm the boundaries of the prototype scope, specifically whether the objective is limited to demonstrating analytical validity and usability, rather than delivering a full production-scale operational system. | Prototype scope boundary | The system is explicitly a prototype-level PoC, not a full production-ready national system. Requests that expand it into broader production or advanced analytics scope should be rejected in favor of the ToR as written.
Q.109 | Section 2.4.8 says payment is strictly performance-based and failure to meet KPIs results in non-payment. Is there any partial payment milestone defined (e.g., after Subsystem A completion, after UAT), or is payment 100% only after all KPIs are met and final handover accepted? | Partial payments / performance-based payment | See answer to Q.42.
Q.110 | The budget ceiling is mentioned but not disclosed. Will JDS disclose the absolute ceiling price before the proposal deadline, or should applicants propose any amount and risk disqualification if exceeding an undisclosed ceiling? | Budget ceiling | See answer to Q.1.
Q.111 | Section 3.2.2 (Forecasting) requires Prophet or ARIMA/SARIMA but does not specify minimum historical data length. What is the minimum number of historical months/years available for training the forecast model at governorate level? | Historical depth and completeness | See answer to Q.23.
Q.112 | Section 3.2.3 (Dashboard) lists “Accessibility rating using transport network data” but Section 3.3 (Out of scope) excludes complex analytics. Should the accessibility rating be implemented in this PoC, or is it optional only if data is readily available without extra development? | Accessibility rating data readiness / optionality; Accessibility rating formula | See answers to Q.27, and Q.30.
Q.113 | The PoC is required to be deployed on-premises at MoTA, with the contractor providing a dedicated server, and with a potential later migration to MoDEE’s internal data center. Could you please confirm if this understanding is correct, and whether public cloud deployment (e.g., Azure, GCP) is not expected or required for this PoC? | Target deployment environment | See answer to Q.81.
Q.114 | If the PoC is successful, is there a planned phase for full-scale system development or continuation with the same vendor? | Future phase / same vendor continuation | The ToR mentions lessons learned and possible future expansion, but it does not commit to a follow-on phase or continuation with the same vendor. Proposals should be scoped only to the current PoC.
Q.115 | Should the server procurement be included within the proposed budget ceiling, or is there a separate allocation for hardware? | Server ownership / hardware handover; Dedicated server requirement | See answers to Q.44, and Q.148.
Q.116 | Is the 6-month timeline fixed, or is there any flexibility depending on data quality or unforeseen challenges? | Timeline flexibility | The timeline is STRICTLY fixed at six months and the PoC must be completed within the JICA project period ending 31 December 2026. The ToR does not permit extending the project period.
Q.117 | Is there a defined budget ceiling for this PoC? | Budget ceiling | See answer to Q.1.
Q.118 | What are the exact KPIs for PoC success and acceptance? | PoC KPIs / acceptance metrics | See answer to Q.5.
Q.119 | How accurate should the forecasting be for acceptance (any KPI defined)? | PoC KPIs / acceptance metrics | See answer to Q.5.
Q.120 | Will you provide official GIS layers (shapefiles, GeoJSON)? | Official GIS layers / GIS-ready reference data | Yes. MoTA/JTB will provide those data.
Q.121 | Are hotel and tourism site datasets geocoded (lat/long), or do we need to map them? | Geospatial data quality / naming consistency; Official GIS layers / GIS-ready reference data | See answers to Q.24, and Q.120.
Q.122 | What happens if datasets are delayed or incomplete at project start? Will timeline or milestones be adjusted accordingly? | If datasets are delayed or incomplete | The datasets are basically already available. The schedule assumes that all input datasets are ready at the beginning of the PoC. The ToR does not provide for schedule extension, so any delay or incompleteness must be managed through early data confirmation, collaboration, and reduced-scope handling where the ToR already allows it.
Q.123 | If major data quality issues (missing, inconsistent, unaligned geo data) impact outputs, how will that affect KPI evaluation and acceptance? | Impact of data quality on KPI evaluation | Data-quality issues should be surfaced in the data assessment, documented in transformation rules, and reflected in the forecast evaluation report and limitations. The ToR does not automatically waive KPIs for poor data, but it does require transparent reporting of limitations and recognizes data constraints and unpredictable events.
Q.124 | What exact datasets will be provided for the PoC? | Exact minimum datasets in scope | The ToR minimum dataset scope covers total visitors; total rooms and beds; average occupancy rate; monthly site visits; monthly hotel occupancy; monthly rooms/beds evolution; national administrative boundaries; major tourism-site locations; and accommodation locations with coordinates where available. See also answer to Q.22
Q.125 | Is the applicant a local company? Or can it be international firm with regional office? | Local vs foreign applicant | The private IT company must be a Jordanian company registered with the CCD with valid relevant licensing. Foreign companies may participate only as consortium members, not leaders, and may not render more than 20% of the work.
Q.126 | In case if the applicant is a joint ventur, is it alright to submit the financial statement of the non local firm? | JV financial statements | The ToR explicitly requires the private IT company to have audited financial statements for the last one year, but it does not spell out the documentation rule for mixed JVs. At minimum, the Jordanian lead/private IT company should provide the required audited statement; any wider JV-document rule should follow the RFP.
Q.127 | Should the reseacher be only in Jordan or a Jordanian nationality? | Researcher based in Jordan vs nationality | The requirement is institutional affiliation in Jordan, not Jordanian nationality. The researcher must be a researcher or professor at a university or research institute in Jordan.
Q.128 | The RFP references an absolute ceiling price (Section 3, Clause 17.2) but does not disclose the amount. Could you indicate the budget ceiling or an indicative range so that applicants can appropriately scope their proposals? | Budget ceiling | See answer to Q.1.
Q.129 | Section 4.1.1 specifies on-premise deployment at MoTA with subsequent migration to MoDEE's data center (Section 4.1.2).Are there data residency requirements that imposes this requirements or would the use of a cloud-based infrastructure (ex. AWS) be acceptable as an alternative or complementary deployment option, provided that all data sovereignty, security, and accessibility requirements are met? | Target deployment environment | See answer to Q.81.
Q.130 | Section 3.2.1(2) references datasets that MoTA/JTB already maintains. Can sample datasets, or at minimum the CSV column definitions and data dictionary, be shared with applicants before proposal submission so that the technical approach in TECH-3 can be precisely scoped? | Sample data / schemas before bid | See answer to Q.22.
Q.131 | Section 3.2.2(6) states that accessibility rating shall be implemented using transport network data provided by MoTA/JTB in GIS-ready format. Can you confirm this data is currently available and specify the format (e.g., shapefile, GeoJSON)? | Accessibility rating data readiness / optionality; Accessibility rating formula | See answers to Q.27, and Q.30.
Q.132 | How many years of historical data are available for tourism demand (visitor arrivals, site visits) and accommodation supply (rooms, beds, occupancy) at MoTA/JTB? | Historical depth and completeness | See answer to Q.23.
Q.133 | Section 4.1.1 requires the contractor to procure and install a dedicated server PC. Will MoTA provide rack space, power, network connectivity, and LAN access for the server at their premises? | Deployment / migration responsibilities | See answer to Q.150.
Q.134 | Section 5.3 requires the academic AI researcher to be affiliated with a university or research institute in Jordan. Is it the responsbility of the Private IT company to search for and select an academic AI researcher to be part of the joint team, or the selection process will be done by MoTA? if it's the private IT company's responsiblity, is there a recommended registry or list of eligible institutions/researchers, or is the selection entirely at the applicant's discretion? | Mandatory joint team and researcher affiliation; Who nominates the academic partner | See answers to Q.20, and Q.186.
Q.135 | Section 3.2.3 specifies the dashboard must be suitable for non-technical policy users at MoTA/JTB. Should the dashboard UI support Arabic language and right-to-left (RTL) layout, or is English sufficient for the PoC? | Arabic / RTL requirement | The ToR does not require Arabic-language or RTL support. English is sufficient for the PoC unless a bidder chooses to add bilingual capability without changing scope, budget, or schedule.
Q.136 | Section 3.2.1(4) requires a repeatable ETL pipeline for monthly data updates. When new data is loaded, should the forecasting model automatically retrain and update all forecast outputs and computed indicators, or should this be a separate manual step triggered by an administrator? | Auto-retrain after upload | The ToR requires monthly data-update procedures and the ability to rerun indicators and forecasts, but it does not require automatic retraining immediately upon upload. A controlled administrator-triggered refresh/recalculation step is consistent with the ToR and is safer for a PoC.
Q.137 | Section 3.2.2(5) describes comparing a single scenario against the forecasted baseline. Should users be able to save multiple scenarios and compare them against each other (e.g., Scenario A vs Scenario B), or is single-scenario-vs-baseline comparison sufficient for the PoC? | Multiple saved scenario comparison | The minimum requirement is comparison of one user-defined scenario against the forecasted baseline for a selected future period.
Q.138 | Section 3.2.3(4) requires an executive summary report exported as PDF. Should this be a fixed-format auto-generated report (one-click export of current dashboard state), or should users be able to select which sections/indicators to include in the report? | PDF report configuration | The ToR only requires an executive-summary PDF including key analytical values and charts; it does not require a fully configurable report builder. A fixed or semi-structured export of the current dashboard state is sufficient for the PoC.
Q.139 | Section 3.4 specifies basic access control (username/password). Should the PoC support multiple user roles (e.g., an administrator role who can upload data and configure thresholds, versus a read-only analyst role who can only view the dashboard and run simulations)? Or is a single shared access level sufficient? | User administration / roles | The minimum requirement is basic username/password access control. Separate administrator role for full credential/system management may be proposed.
Q.140 | Existing Systems and Data Repositories Could you please provide details on the current systems and platforms that host relevant datasets (e.g., GIS platforms, tourism databases, infrastructure systems, statistical repositories)? | Existing systems / repositories | The ToR indicates that relevant data already exists at MoTA/JTB and is currently analyzed across multiple spreadsheets and reports rather than within one unified platform. No detailed inventory of current systems/repositories is provided, and the PoC must remain standalone.
Q.141 | Data Types and Formats What types of data are currently available (e.g., spatial/vector, raster, tabular, real-time feeds), and in what formats are they maintained? | Data types and formats | Expected data is primarily structured tabular tourism statistics, especially CSV exports, plus GIS-ready vector layers such as administrative boundaries and point locations. The ToR does not require raster or real-time feed integration.
Q.142 | Data Structure and Standards Are there existing data models, schemas, or standards in place that govern how data is structured, classified, and maintained? | Data models / standards / naming rules | The system must standardize to consistent governorate/region names and IDs, monthly time indices, and MoTA/JTB naming standards where available. No complete pre-existing enterprise data model is provided in the ToR, so Subsystem A must establish the harmonized analysis-ready schema.
Q.143 | Data Sources and Ownership Could you clarify the primary sources of data (e.g., government entities, private sector, third-party providers), and any associated ownership or access constraints? | Data sources and ownership | Core data is to come from MoTA/JTB for use in the PoC. The developed PoC solution delivered under the project, including datasets/scripts/source code in the delivered package, belongs to MoTA.
Q.144 | Existing Integrations Are there any current integrations between systems (e.g., APIs, data warehouses, enterprise platforms) that we should consider as part of the PoC? | Data exchange method / integrations; Existing systems / repositories | See answers to Q.4, and Q.140.
Q.145 | Data Gaps and Quality Are there known gaps, inconsistencies, or quality issues in the available datasets that should be accounted for in the proposal? | Geospatial data quality / naming consistency; Impact of data quality on KPI evaluation | See answers to Q.24, and Q.123.
Q.146 | Data Acquisition Responsibilities Please clarify whether the selected contractor is expected to: | Data acquisition responsibility | See answer to Q.147.
Q.147 | Perform data collection or entry activities, Source or procure data from external public or private entities, or Work solely with datasets provided by the client. Data Governance and Security Requirements Are there specific data governance policies, security requirements, or compliance standards that must be adhered to? | Data acquisition responsibility | The contractor is to work with datasets already available at MoTA/JTB; acquiring or generating new data is explicitly out of scope. The contractor is responsible for cleaning, harmonization, ETL, and use of the provided data.
Q.148 | Regarding the requirement to procure a PC for the PoC, could you confirm whether the specifications provided are mandatory or indicative, and could you clarify the expected ownership and handover process of the PC after project completion? | Dedicated server requirement | The specification of PC in the ToR is indicative. The ownership of the PC will be handed to MoTA at the end of this PoC.
Q.149 | In cases where the contractor determines that the PoC system can be effectively developed and deployed using existing hardware resources (e.g., Government-provided laptops), would it be acceptable to utilize such resources instead of procuring new ones? | Dedicated server requirement | See answer to Q.148.
Q.150 | Could you clarify the expected deployment and migration process to MoDEE's infrastructure, including the contractor’s responsibilities during transition from the staging environment? | Deployment / migration responsibilities | See answer to Q.32 and Q.33.
Q.151 | Would it be acceptable for the PoC to be developed within the contractor’s environment (e.g. PwC systems), with subsequent deployment and integration as required? | Development in contractor environment | Development may occur in the contractor's own environment, but the delivered PoC must ultimately be deployed on-premise at MoTA and then migrated to MoDEE as required by the ToR. Any interim contractor-hosted setup cannot replace the mandated target deployment.
Q.152 | Could you clarify the expected responsibilities between MoTA and the contractor for the installation, configuration, testing, and deployment of systems and services on the procured PC, including security setup and the time required to install? | Deployment / migration responsibilities | See answer to Q.150.
Q.153 | Could you confirm whether the "absolute ceiling of budget" will be disclosed prior to submission, or if any indicative budget range can be shared? And will negotiations occur before autodisqualification? | Budget ceiling | See answer to Q.1.
Q.154 | In case audited financial statements cannot be disclosed for confidentiality and sensitivity, would alternative documents (e.g., annual reports) be considered acceptable? | Alternative to audited financial statements | The ToR specifically requires an audited financial statement for the last one year. No alternative documents are permitted.
Q.155 | In reporting the “number of engineers”, could you clarify whether this should reflect the total company workforce, or only the team relevant to the PoC project? | Reporting the number of engineers | The ToR's operative requirement is the existence of a major IT development team in Jordan rather than a purely corporate headcount statistic.
Q.156 | Could you confirm whether all required datasets are readily available and will be provided at the start of the project? | Assumption about dataset sufficiency / readiness | See answer to Q.61.
Q.157 | At what level is tourism data collected (e.g. hotel, site, city, country), and what structured attributes (e.g. facilities) and spatial data (e.g. polygon boundaries for sites) are available? | Geographic granularity; Exact minimum datasets in scope | See answers to Q.91, and Q.124.
Q.158 | Could you confirm whether the MoTA datasets are expected to be completely in digital, structured format? (e.g. excel tables) | Data types and formats; Data exchange method / integrations | See answers to Q.141, and Q.4.
Q.159 | Are there any known data quality limitations or gaps that should be considered during implementation? | Geospatial data quality / naming consistency; Impact of data quality on KPI evaluation | See answers to Q.24, and Q.123.
Q.160 | Beyond accommodation capacity (hotels, rooms, beds), are there additional tourism-related infrastructure dimensions (e.g., public buses) that could be considered within the PoC scope? | Additional tourism infrastructure dimensions | No additional multi-sector or broader infrastructure dimensions should be assumed. The PoC scope focuses on tourism demand, accommodation capacity, GIS context, and only limited transport-based accessibility where data is readily available at MoTA/JTB.
Q.161 | How many years of monthly data does MoTA have, and is it continuous or patchy? | Historical depth and completeness | See answer to Q.23.
Q.162 | Is the bed addition in the simulation a single point-in-time change, or can it be phased across months? | Simultaneous / phased scenarios | See answer to Q.29.
Q.163 | Will MoTA define the occupancy/capacity index formulas, or should we propose them for approval? | Indicator formulas / thresholds / approval | See answer to Q.77.
Q.164 | Configurable thresholds — live UI recalculation or config file + pipeline re-run? | Configuring thresholds / rules; Indicator formulas / thresholds / approval | See answers to Q.178, and Q.77.
Q.165 | Is the cultural/nature/coastal/religious site classification already in MoTA's data, or do we need to build it? | Destination-type classification | Yes
Q.166 | Has the GIS transport network data (roads + airline routes) been confirmed as ready to hand over? | Accessibility rating data readiness / optionality | See answer to Q.27.
Q.167 | Could you please clarify whether the scope of the PoC allows for the use of enterprise-level platforms, or if the solution is expected to be strictly based on open-source tools? And what is the forecasted plan in case of a successful PoC,Does it include using the same licenses or tools to rollout ? | Open-source vs proprietary / enterprise tools; Future phase / same vendor continuation | See answers to Q.45, and Q.114.
Q.168 | Does the Entity already have access to all the data sources stated in the document and the scope inlcudes only the stated datasources. Also what is the expected integration method (API, etc.. )? | Data exchange method / integrations; Data acquisition responsibility; Assumption about dataset sufficiency / readiness | See answers to Q.4, Q.147, and Q.61.
Q.169 | Are historical datasets sufficient for forecasting (minimum 2–3 years monthly data)? | Historical depth and completeness | See answer to Q.23.
Q.170 | Could you advise on the expected quality of the datasets, particularly in terms of:Missing values,Inconsistent naming conventions (e.g., regions, sites),Data gaps or incomplete records | Geospatial data quality / naming consistency; Impact of data quality on KPI evaluation | See answers to Q.24, and Q.123.
Q.171 | Should the PoC include data cleaning, transformation, and validation as part of the core scope, or is the primary focus expected to be on forecasting and analytics using pre-prepared data? | Data cleaning and ETL responsibility | See answer to Q.3.
Q.172 | Kindly confirm the types and structure of data that will be provided (e.g., structured, semi-structured, or unstructured), along with the expected data formats. | Data types and formats | See answer to Q.141.
Q.173 | Is simulation expected to be Real-time, or batch-based calculation acceptable? | Minimum scenario / simulation scope | See answer to Q.80.
Q.174 | Can the PoC be implemented using enterprise tools (e.g., SAS data pipelines) instead of Python-based scripts, provided all transformation logic is documented and reproducible? | Open-source vs proprietary / enterprise tools | See answer to Q.45.
Q.175 | Can the PoC be implemented using an enterprise analytics platform for the core analytics and data processing engine, while still ensuring interoperability with open-source components where required? | Open-source vs proprietary / enterprise tools | See answer to Q.45.
Q.176 | For the scenario-based simulation: Is a rule-based recalculation approach sufficient, Or is there an expectation for a more advanced decisioning or optimization-driven simulation engine? | Minimum scenario / simulation scope | See answer to Q.80.
Q.177 | Kindly confirm the expected number and roles of users: Analysts, Business users,Admins | Expected user groups | See answer to Q.31 and Q.139.
Q.178 | Should business users be able to configure simulation parameters and rules through the UI, or is backend configuration acceptable? | Configuring thresholds / rules | The ToR requires that thresholds and scoring rules be configurable by MoTA analysts, but it does not require a complex end-user rules engine. A simple admin-oriented configuration screen or controlled backend configuration is acceptable for the PoC.
Q.179 | Number of Dashboards needed for the PoC per scenario stated? | Required dashboard pages | See answer to Q.102.
Q.180 | Kindly confirm if there are any specific GIS platforms that need to be integrated as part of the solution? | Need to integrate specific GIS platforms | No integration with specific existing GIS platforms is required. The contractor should choose and justify a standalone open-source GIS/dashboard architecture consistent with the ToR.
Q.181 | Can the delivery mode for this PoC be Offshore or is On-Premises mandatory ? | Target deployment environment | See answer to Q.81.
Q.182 | Will MoTA provide Rack space, power, networking Or is full setup responsibility on vendor? | Deployment / migration responsibilities | See answer to Q.150.
Q.183 | Are there any constraints or preferences regarding: Licensed enterprise platforms vs fully open-source solutions? | Open-source vs proprietary / enterprise tools | See answer to Q.45.
Q.184 | Will the target environment support Container orchestration (Kubernetes)? | Containerization / Kubernetes | The ToR does not specify Kubernetes or any container-orchestration requirement. Containerization may be used if it supports the mandated on-prem/MoDEE deployment and full handover, but bidders should not assume orchestrator availability in the target environment.
Q.185 | Could you confirm whether the AI academia partner must be a formal institution, or if qualified individuals (e.g., researchers or domain experts) can fulfill this requirement? | Whether the academic partner must be a formal institution | See answer to Q.20.
Q.186 | The scope mentions the involvement of a Jordan-based academic partner specializing in AI. Could you please confirm whether this partner is expected to be nominated by your team? | Who nominates the academic partner | It is the applicant Joint Team's responsibility to form the required partnership before bidding.
Q.187 | For the required on-premise server, could you specify the minimum hardware requirements, including CPU cores, RAM, and storage specifications, to ensure accurate financial estimation and system performance? | Server spec | See 4.1.1. of ToR
Q.188 | Will the datasets from MoTA and JTB be provided as static files, or will API or database access be available to support automated data integration and ETL processes? | Data accessibility | See answer of Q.4
Q.189 | How many years of historical tourism data will be made available for analysis, particularly to support accurate seasonality and demand modeling? | Historical depth and completeness | See answer of Q.23
Q.190 | Is there an existing predefined methodology or formula for calculating the Gap Index and Investment Priority indicators, or is the development of this methodology expected as part of the project scope? | Methodology for indicators | See answer of Q.76.
Q.191 | Are there any specific branding or visual identity guidelines that should be followed for the GIS dashboard design? | Design guideline | See answer of Q.84.
Q.192 | Will the system require role-based access control, such as different user permissions for administrators and viewers, or will it function as an open internal tool? | User administration / roles | See answer of Q.139.

## Data columns
Dataset | column | type | example
Site Visitors | Year | Number | 2011
Site Visitors | MonthName | String | October
Site Visitors | Sites_ArabicName | String | KERAK
Site Visitors | Region_Ar_New | String | الأجانب
Site Visitors | Nat_Arabic_Aliase | String | اخرى امريكي
Site Visitors | TotalSitesTourists | Number | 125